## Sheet1
# | Task | Estimated Hours | Status | Note
1 | Database Design | 6 | Completed |  |  |  | Login and Logout tasks wasn't mentioned here but they also completed
2 | Projet setup & theme integration | 6 | Completed |  | Estimated start date | 2020-11-25
3 | Create account (first name, last name, email, register as [recruiter, athlete], password) | 8 | Completed |  | Estimated end date | 2020-12-02
Profile
4 | Edit Detail (first name, last name, height, weight, class of, sport position(s), school, address, about me, contact phone number, sicial media links) | 12 | Completed
| Recruiter Profile Update [columns => title, fax, school/college/team] (As per discussed on call) | 7
5 | Add/Update profile pic | 4 | Completed
6 | News feed (add post like facebook) | 16 | TBD
7 | Add/Update My top schools | 5 | TBD |  | Estimated start date | 2020-12-04
8 | My transcripts (add transript, make trascript public or give access to someone) | 5 | TBD |  | Estimated end date | 2020-12-13
9 | Add/Update GPA | 4 | TBD
10 | Add/Update reference teams (scale of 1-10) | 0 | TBD | Duplicate Task# 7
11 | Add/Update Commit Status Drop down (undecided, verbal commit, commited) | 4 | TBD
12 | Add Feedback How could we improve your experience? (Free form text box) | 5 | TBD
Search School
13 | Select college (s) from dropdown | 5 | TBD
14 | Select sport Listing of Coach/Administrator title, email, and phone with a check box to select the person's info. "Email my profile" to the person with a check box that has been checked | 8 | TBD
15 | Users can mark their level of interest in College/University (scale of 1 - 10) | 3 | TBD |  | Estimated start date | 2020-12-14
16 | Feedback How could we improve your experience? (Free form text box) | 0 | TBD | Duplicate Task#12 | Estimated end date | 2020-12-19
Search Athlete
17 | Search criteria First name Last name Height Weight Class of (drop-down menu) Sport Position Add another position, Add another sport, Team Interest, Lives Search by Social Media Names (Facebook, Instagram, TikTok, LinkedIn) | 8 | TBD
18 | Favorites Ability to create favorite list | 6 | TBD
19 | Ability to email player profile to yourself | 6 | TBD
20 | Feedback How could we improve your experience? (Free form text box) |  | TBD | Duplicate Task#12 & 16 | Estimated start date | 2020-12-20
21 | Testing & Deployment | 6 | TBD |  | Estimated end date | 2020-12-26
124
Note: If there is any change occurred in requirements, we have to change the plan accordingly as well (Both time & cost)
Note on A1: Login, Logout tasks wasn't mentioned here. But they also completed -Hassan Raza
Note on B4: Add "scout" as filter -WreckWrim
Note on B6: User can select "pro candidate/not in school" if "class of..." doesn't apply -WreckWrim